## Risks
Stockupy Stock Management System Risk List
Risk ID | Date Identified | Headline | Description | Type | Impact | Probability | Magnitude | Owner | Mitigation Strategy
1 | 11.04.2021 | Requirements Inflation | The concepts, requirements, number of tasks in a sprint and priorities of tasks can change during the project. When a requirement changes or new requirements are offered, it significantly impacts the ability of the developers to stick to the original timeline of a project. | Schedule | 5 | 70% | 3.5 | P.O. & P.M. | Considering how it would affect the project's current state, how much work it will need, and whether there is a chance of delays. This analysis would allow for efficient task division, updating priorities, and providing accurate information about what can be provided.
2 | 11.04.2021 | Lack of communication | Communication is essential for a software development project's efficiency. Misunderstandings in the workflow, low return on investment and even revenue loss result from a lack of or poor communication. | Resource | 2 | 50% | 1 | Stakeholders | All stakeholders should meet on a regular basis to complete tasks and share information gained through the project.
3 | 11.04.2021 | Employee Turnover | When key staff exit the project, they take sensitive details with them, causing the project to be greatly delayed. | Resource | 4 | 25% | 1 | P.M. | To reduce the impact of this risk, agile projects use information-sharing strategies like pair programming, shared code ownership, and regular reporting at daily stand-ups.
4 | 11.04.2021 | Poor documentation | Mismanaged documentation and workflows result in an increase in project costs and falling behind schedule. | Technical | 4 | 80% | 3.2 | P.M. & Dev. Team & P.O. | Using tools such as JIRA and Redmine, task definitions are made properly and version controls and changes are tracked by using Github and Sourcetree. Thus, information is always accessible by everyone and the time required to access and search it can be shortened.
5 | [6 empty] | 0
6 | [6 empty] | 0
7 | [6 empty] | 0
8 | [6 empty] | 0
9 | [6 empty] | 0
10 | [6 empty] | 0
11 | [6 empty] | 0
12 | [6 empty] | 0
13 | [6 empty] | 0
14 | [6 empty] | 0
15 | [6 empty] | 0
16 | [6 empty] | 0
17 | [6 empty] | 0
18 | [6 empty] | 0