## Sheet1
Name / Description | Priority | Size estimate (Points) | State | Target iteration | Assigned To | Effort estimate left (hours) | Hours worked | Reference material
Produce draft vision | 1 | 1 | Closed | 0 | Berfu Esra Nehir Özgün | 0 | 8 | <Vision.doc>
Produce Work Items List | 1 | 1 | Closed | 1 | Nehir | 0 | 2 | <work items list.xls>
Write all use cases in brief format | 1 | 10 | Closed | 1 | Esra | 0 | 9 | <Use-case Specification.doc>
Revise the Vision | 1 | 1 | Closed | 1 | Berfu Esra Nehir Özgün | 0 | 4 | <Vision.doc>
Produce Project Plan v1.0 | 1 | 9 | Closed | 1 | Berfu Nehir | 0 | 9 | <Project Plan.doc>
Initiate Risk List v1.0 | 1 | 4 | Closed | 1 | Berfu | 0 | 4 | <Risk List.xls>
Initiate System-Wide Requirements v1.0 | 1 | 4 | Closed | 1 | Berfu Esra Nehir Özgün | 0 | 4 | <System-Wide Requirements.doc>
Initiate Glosarry v1.1 | 1 | 1 | Closed | 1 | Berfu Nehir | 0 | 2 | <Glossary.doc>
Write fully-dressed Use Case for UC1.2 and UC2.1 | 1 | 6 | Closed | 1 | Esra | 0 | 5 | <Use-case Specification.doc>
Write Initial version of plan for Iteration II | 1 | 3 | Closed | 1 | Berfu Nehir | 0 | 2 | <Iteration Plan II.doc>
Reviewed the plan for Iteration II | 1 | 4 | Closed | 1 | Berfu Esra | 0 | 2 | <Iteration Plan II.doc>
Implement Use Case UC1.2 | 1 | 20 | Closed | 2 | Berfu Özgün | 0 | 10 | <Use-case Specification.doc>
Write Test Cases for UC1.2 | 2 | 4 | Closed | 2 | Nehir | 0 | 2 | <Test Cases.doc>
Write fully-dressed Use Case for UC2.2 and UC2.3 | 1 | 6 | Closed | 2 | Esra | 0 | 5 | <Use-case Specification.doc>
Deliver Risk List v1.1 | 1 | 2 | Closed | 2 | Berfu | 0 | 1 | <Risk List.xls>
Deliver Project Plan v1.1 | 1 | 2 | Closed | 2 | Berfu | 0 | 1 | <Project Plan.doc>
Deliver System-Wide Requirements v1.1 | 1 | 2 | Closed | 2 | Berfu Esra Nehir Özgün | 0 | 1 | <System-Wide Requirements.doc>
Deliver Glossary v3.0 | 1 | 2 | Closed | 2 | Esra | 0 | 1 | <Glossary.doc>
Initiate Design Document for UC1.2 and UC2.1 v1.0 | 1 | 3 | Closed | 2 | Berfu Özgün | 0 | 6 | <Design.doc>
Initiate Architecture Notebook v1.0 | 1 | 3 | Closed | 2 | Özgün | 0 | 6 | <Architecture Notebook.doc>
Write Initial version of plan for Iteration III | 1 | 3 | Closed | 2 | BerfuEsra Esra | 0 | 2 | <Iteration Plan III.doc>
Write fully-dressed All Use Cases | 1 | 12 | New | 3 | Esra | 15 | 0 | <Use-case Specification.doc>
Deliver Glossary v3.1 | 1 | 2 | New | 3 | Esra | 5 | 0 | <Glossary.doc>
Implement Use Case UC1.2 Extensions | 1 | 5 | New | 3 | Berfu Özgün | 2 | 0 | <Use-case Specification.doc>
Implement Use Case UC2.1 and 2.3 | 1 | 20 | New | 3 | Berfu Özgün | 10 | 0 | <Use-case Specification.doc>
Write test cases for UC2.1 and UC2.3 | 1 | 5 | New | 3 | Nehir | 5 | 0 | <Test Cases.doc>
Produce Design Document for UC2.1 and UC2.3 v2.0 | 1 | 3 | New | 3 | Berfu Özgün | 6 | 0 | <Design.doc>
Revised Architecture Notebook | 1 | 3 | New | 3 | Özgün | 6 | 0 | <Architecture Notebook.doc>
Write Initial version of plan for Iteration IV | 1 | 3 | New | 1 | Berfu Nehir | 2 | 0 | <Iteration Plan IV.doc>